## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2201-swen-261-09-s1d-labrats
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | RRC; 09/24 | Pass | RRC; 10/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | RRC; 09/24 | Pass | RRC; 10/18
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | RRC; 09/24 | Pass | RRC; 10/18
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | RRC; 09/24 | Pass | RRC; 10/18
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | RRC; 09/25 | Pass | RRC; 10/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | RRC; 09/24 | Pass | RRC; 10/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | RRC; 09/24 | Pass | RRC; 10/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | RRC; 09/30 | Pass | RRC; 10/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | RRC; 09/30 | Pass | RRC; 10/18
As a Player, I want to sign out, so I don't have to worry about people starting games against me. | Given I am at the home page, when I click on the sign out button, then I should be signed out of Web Checkers |  |  | Pass | Sokol; 10/18
| Given I am signed out when someone loads the home page then my name should not appear |  |  | Pass | Sokol; 10/18
As a Player I want the game to take turns so that it is a fair game. | Given it is my turn to move when I submit a move then it should no longer be my turn |  |  | Pass | Sokol; 10/09
| Given I am playing a game of Checkers when it is not my turn then it should be the other player's turn |  |  | Pass | Sokol; 10/09
| Given it is not my turn when it becomes my turn then I should get a turn |  |  | Pass | Sokol; 10/09
| Given I am playing a game of Checkers when it is my turn then I should be allowed to make a move |  |  | Pass | Sokol; 10/09
| Given I am player a game of Checkers when it is not my turn then I should not be able to make a move or resign |  |  | Pass | Sokol; 10/09
| Given I am playing a game of Checkers when it is my turn then I should be allowed to resign |  |  | Pass | Sokol; 10/09
As a Player I want the game to end so I can do other things. | Given I am in a game when the game ends then the end game button will appear. |  |  | Pass | Sokol; 10/15
| Given I click the "End Game" button when the game is over, then I should be sent to the home page |  |  | Pass | Sokol; 10/15
| Given I am in a game when the game is over, then the buttons other than the End Game button should disappear |  |  | Pass | Sokol; 10/15
| Given the game is over when I try to move a piece, then it should not move |  |  | Pass | Sokol; 10/15
| Given I am in a game when the game ends then I should see a message explaining why the game is over. |  |  | Pass | Sokol; 10/15
As a Player I want to be able to end the game so I can get back to my life. | Given I click a resign button when I am in the middle of a game then I expect the game to end. |  |  | Pass | Sokol; 10/18
As a Player I want to move so that I can play the game. | Given I choose a valid position where I move forward one space diagonally and no pieces are in my way when I try to move the piece then I expect the piece to move. |  |  | Pass | Sokol; 10/05
| Given I choose an invalid position when I try to move my piece then the piece should not move. |  |  | Pass | Sokol; 10/05
| Given I have moved a piece without submitting when I click Backup Move, then my move should be reverted. |  |  | Pass | Sokol; 10/05
| Given I have moved a piece without submitting when I click Submit Move, then my move should be submitted. |  |  | Pass | Sokol; 10/05
As a Player I want to jump over opponent pieces so I can make progress in the game. | Given that I try to jump over an adjacent piece when I move then I expect to capture that piece. |  |  | Pass | RRC; 10/12
| Given that a move is being made when a piece is captured then the piece should be removed from the board |  |  | Pass | RRC; 10/12
| Given that I am able to capture another piece when a piece has been captured then I expect to be allowed to make another jump |  |  | Pass | RRC; 10/12
| Given that a piece is on the other side of a piece I want to capture when I try to capture the piece then it should not validate the move |  |  | Pass | RRC; 10/12
As a Player I want to get kings so I can have more mobility. | Given my piece is a king when it is my turn to move then I should be allowed to move the piece backward |  |  | Pass | Sokol; 10/13
| Given I reach the opposite side of the board when I move my piece then I expect to gain a king. |  |  | Pass | Sokol; 10/13
As a Player I want to win so I can say I accomplished something in life. | Given I have captured all opposing pieces when I play the game then I expect to be told that I won. |  |  | Pass | Sokol; 10/18
| Given I am playing a game of Checkers when I win then the game should end |  |  | Pass | Sokol; 10/18
As a Player I want to adjust the difficulty of the AI so I have a chance at beating it. | Given I select a difficulty when I am about to play a a game then I expect the AI to play at that level.
Given I am signed in when I am at the home page then I expect to see all the AI players.
Given I am on the home screen when I click on an AI player then I should be brought into a game.
As a Player I want to play against an AI so I don’t have to find a human to play against. | Given I am playing against an AI when I make a move then an opponent move should be made automatically.
As a user I want to watch other peoples’ games so that I can see what other players are doing. | Given I am signed in when I am at the home screen then I expect to see a list of currently active games that I can watch.
Given that I am at the home screen when I click on a currently active game then I expect to be sent into spectator mode.
Given that I am in spectator mode when a player in the game makes a move then I expect to see the result of the move.
Given I am in spectator mode when I click Exit then I expect to leave the game.
As a Player I want to help button so that play optimally.
As a Player I want to see how many pieces I've won or lost so that I know how I'm doing.